## 2013-08-05
ID | Sev | Pri | OS | Assignee | Status | Summary
2437 | cri | P1 | Othe | arlin.r.davis@intel.com | NEW | "DAPL" transaction test fails with "error: DAT_CONN_QUAL_IN_USE"
2400 | maj | P2 | Othe | arlin.r.davis@intel.com | ASSI | Dapltest fails to run with -T 16 and -w 8 option with DAT_INVALID_STATE error.
2418 | nor | P5 | Othe | arlin.r.davis@intel.com | NEW | dapltest with 100000 iterations and 150 threads hangs and packets do not transfer between client and server
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16
2416 | nor | P5 | Othe | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config
2423 | maj | P5 | Othe | idos@dev.mellanox.co.il | NEW | ib_atomic_lat with -R and -z options fails
2419 | maj | P5 | Othe | idos@dev.mellanox.co.il | NEW | ib_write_bw -R and -z options fail in OFED-3.5
2422 | maj | P5 | Othe | idos@dev.mellanox.co.il | NEW | ib_atomic_bw with -R and -z options fails
2420 | maj | P5 | Othe | idos@dev.mellanox.co.il | NEW | ib_read_lat with -R and -z options fail in OFED-3.5
2427 | nor | P5 | Othe | jackm@mellanox.co.il | NEW | flood of MLX4_EVENT_TYPE_SRQ_LIMIT in dmesg
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails
2411 | maj | P5 | RHEL | jackm@mellanox.co.il | NEW | 3.5-rc5 RH 6.3 kernel panics on boot kernel 3.4.[22 ¦ 24 ¦ 27]
2375 | enh | P2 | SLES | tom@opengridcomputing.com | NEW | NFSoRDMA support required for SLES11sp2, RHEL6u2 & RHEL6u3.
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version.
2406 | maj | P1 | Othe | vipul@chelsio.com | ASSI | "command 0x16 in mailbox 4 timed out" error seen while running OpenMPI along with MTU change.
2373 | nor | P3 | Othe | vlad@mellanox.co.il | NEW | Many Packages are reported Unsupported while doing complete installation of OFED-3.5 using " ./install.pl -c ofed-all.conf " command.
2403 | maj | P1 | Othe | vlad@mellanox.co.il | NEW | OFED installation is failing on freshly installed RHEL6.2 os.
2421 | maj | P2 | Othe | vlad@mellanox.co.il | NEW | redefined error in 2.6.32-279.22.1.el6.x86_64 kernel
2432 | nor | P5 | All | vlad@mellanox.co.il | NEW | Reinstalling OFED-3.5 removes openmpi
2436 | maj | P5 | RHEL | vlad@mellanox.co.il | NEW | OFED-3.5.1-20130522-0954 duplicate symbol error with 2.6.32-358.11.1.el6.x86_64
2413 | maj | P5 | SLES | vlad@mellanox.co.il | NEW | compat: exports duplicate symbol ida_simple_get (owned by kernel) sles11sp2
2417 | maj | P5 | Othe | vlad@mellanox.co.il | NEW | Error compiling compat-rdma on Centos 6.4
2431 | tri | P5 | All | vlad@mellanox.co.il | NEW | Copyright in compat-rdma refers to Openib.org
2415 | nor | P5 | Cent | weiny2@llnl.gov | NEW | [OFED-3.5] infiniband-diags fails to build on Centos 6.3/6.4

## 2013-09-15
ID | Sev | Pri | OS | Assignee | Status | Summary
2418 | nor | P5 | Other | arlin.r.davis@intel.com | NEW | dapltest with 100000 iterations and 150 threads hangs and packets do not transfer between client and server
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2
2422 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails
2419 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5
2423 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails
2420 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5
2415 | nor | P5 | Cent | ira.weiny@intel.com | ASSI | [OFED-3.5] infiniband-diags fails to build on Centos 6.3/6.4
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails
2375 | enh | P2 | SLES | tom@opengridcomputing.com | NEW | NFSoRDMA support required for SLES11sp2, RHEL6u2 & RHEL6u3.
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version.
2403 | maj | P1 | Other | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os.
OFED 3.5
ID | Sev | Pri | OS | Assignee | Status
2418 | nor | P5 | Other | arlin.r.davis@intel.com | NEW
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW
2422 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP
2419 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP
2423 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP
2420 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP
2415 | nor | P5 | Cent | ira.weiny@intel.com | ASSI
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW
2375 | enh | P2 | SLES | tom@opengridcomputing.com | NEW
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW
2403 | maj | P1 | Other | vlad@mellanox.co.il | ASSI
OFED 3.5-2
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors seen while running test.
2439 | maj | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapl Pipeline test with RDMA Write and scatter gather list fails
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress.

## 2013-09-30
ID | Sev | Pri | OS | Assignee | Status | Summary
2418 | nor | P5 | Othe | arlin.r.davis@intel.com | NEW | dapltest with 100000 iterations and 150 threads hangs and packets do not transfer between client and server
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16
2416 | nor | P5 | Othe | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2
2419 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5
2423 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails
2420 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5
2422 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails
2415 | nor | P5 | Cent | ira.weiny@intel.com | ASSI | [OFED-3.5] infiniband-diags fails to build on Centos 6.3/6.4
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails
2375 | enh | P2 | SLES | tom@opengridcomputing.com | NEW | NFSoRDMA support required for SLES11sp2, RHEL6u2 & RHEL6u3.
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version.
2403 | maj | P1 | Othe | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os.
OFED 3.5
ID | Sev | Pri | OS | Assignee | Status | Summary
2418 | nor | P5 | Other | arlin.r.davis@intel.com | NEW | dapltest with 100000 iterations and 150 threads hangs and packets do not transfer between client and server | Woody has forwarded to Arlin
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16 | Woody has forwarded to Arlin
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config | Vlad will review with his developers
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2 | Vlad will review with his developers
2419 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5 | Vlad will review with his developers
2423 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails | Vlad will review with his developers
2420 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5 | Vlad will review with his developers
2422 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails | Vlad will review with his developers
2415 | nor | P5 | Cent | ira.weiny@intel.com | ASSI | [OFED-3.5] infiniband-diags fails to build on Centos 6.3/6.4 | Rupert
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails | Vlad will review with his developers
2375 | enh | P2 | SLES | tom@opengridcomputing.com | NEW | NFSoRDMA support required for SLES11sp2, RHEL6u2 & RHEL6u3. | Steve - he is not maintainer - Jeff Becker
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version. | Steve will contact vipul - he will find a way to prepend version with OFED. Since upstream it has -ko
2403 | maj | P1 | Other | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os. | Vlad will review with his developers
OFED 3.5-1
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | NEW | duplicate member error when building infinipath-psm-3.1-364.1140 | Tom - he is working on this and is close to a fix. They did not include this in last update.
OFED 3.5-2
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors seen while running test.
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic)
2439 | maj | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapl Pipeline test with RDMA Write and scatter gather list fails
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress. | Steve assigned to vipul - may be resolved in libcxb4
2446 | maj | P5 | RHEL | tom@opengridcomputing.com | NEW | Loading the modules xprtrdma and svcrdma are failing after installing OFED-3.5-2-rc1.tgz | This is a simple change - says NFSoRMDA - change it to available. Probably in install.pl
2449 | maj | P5 | RHEL | tom@opengridcomputing.com | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 release | Predeep - the install.pl was not compiling NFSoRDMA for OFED.
Core dump on x86 for Dapl.
Notes
Vlad - may need to do for other OS

## 2013-10-13
ID | Sev | Pri | OS | Assignee | Status | Summary
2418 | nor | P5 | Othe | arlin.r.davis@intel.com | NEW | dapltest with 100000 iterations and 150 threads hangs and packets do not transfer between client and server
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16
2416 | nor | P5 | Othe | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2
2419 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5
2423 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails
2420 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5
2422 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails
2415 | nor | P5 | Cent | ira.weiny@intel.com | ASSI | [OFED-3.5] infiniband-diags fails to build on Centos 6.3/6.4
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails
2375 | enh | P2 | SLES | tom@opengridcomputing.com | NEW | NFSoRDMA support required for SLES11sp2, RHEL6u2 & RHEL6u3.
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version.
2403 | maj | P1 | Othe | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os.
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | 2013-09-29 | 2013-10-13 | Change
2418 | nor | P5 | Other | arlin.r.davis@intel.com | NEW | dapltest with 100000 iterations and 150 threads hangs and packets do not transfer between client and server | NEW | NEW | No
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16 | NEW | NEW | No
2375 | enh | P2 | SLES | becker@nas.nasa.gov | NEW | NFSoRDMA support required for SLES11sp2, RHEL6u2 & RHEL6u3. | NEW | NEW | No
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config | NEW | NEW | No
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2 | NEW | NEW | No
2419 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5 | REOP | REOP | No
2420 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5 | REOP | REOP | No
2422 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails | REOP | REOP | No
2423 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails | REOP | REOP | No
2415 | nor | P5 | Cent | ira.weiny@intel.com | ASSI | [OFED-3.5] infiniband-diags fails to build on Centos 6.3/6.4 | ASSI | FIXED | Yes
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails | NEW | NEW | No
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version. | NEW | NEW | No
2403 | maj | P1 | Other | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os. | NEW | NEW | No
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | 2013-09-29 | 2013-10-13 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | NEW | duplicate member error when building infinipath-psm-3.1-364.1140 | NEW | NEW | No
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | 2013-09-29 | 2013-10-13 | Change
2439 | maj | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapl Pipeline test with RDMA Write and scatter gather list fails | NEW | NEW | No
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors seen while running test. | NEW | NEW | No
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) | NEW | NEW | No
2446 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Loading the modules xprtrdma and svcrdma are failing after installing OFED-3.5-2-rc1.tgz | NEW | FIXED | Yes
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | NEW | NEW | No
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress. | ASSI | ASSI | No

## 2013-10-22
ID | Sev | Pri | OS | Assignee | Status | Summary
2418 | nor | P5 | Othe | arlin.r.davis@intel.com | NEW | dapltest with 100000 iterations and 150 threads hangs and packets do not transfer between client and server
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16
2416 | nor | P5 | Othe | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2
2419 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5
2423 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails
2420 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5
2422 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails
2415 | nor | P5 | Cent | ira.weiny@intel.com | ASSI | [OFED-3.5] infiniband-diags fails to build on Centos 6.3/6.4
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails
2375 | enh | P2 | SLES | tom@opengridcomputing.com | NEW | NFSoRDMA support required for SLES11sp2, RHEL6u2 & RHEL6u3.
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version.
2403 | maj | P1 | Othe | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os.
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | 2013-10-13 | 2013-10-22 | Change
2375 | enh | P2 | SLES | becker@nas.nasa.gov | NEW | NFSoRDMA support required for SLES11sp2, RHEL6u2 & RHEL6u3. | NEW | FIXED | Yes
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version. | NEW | NEW | No
2403 | maj | P1 | Other | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os. | NEW | ASSI | Yes
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config | NEW | NEW | No
2418 | nor | P5 | Other | arlin.r.davis@intel.com | NEW | dapltest with 100000 iterations and 150 threads hangs and packets do not transfer between client and server | NEW | FIXED | Yes
2419 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5 | REOP | REOP | No
2420 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5 | REOP | REOP | No
2422 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails | REOP | REOP | No
2423 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails | REOP | REOP | No
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16 | NEW | NEW | No
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails | NEW | NEW | No
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2 | NEW | NEW | No
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | 2013-10-13 | 2013-10-22 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | NEW | duplicate member error when building infinipath-psm-3.1-364.1140 | NEW | NEW | No
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | 2013-10-13 | 2013-10-22 | Change
2439 | maj | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapl Pipeline test with RDMA Write and scatter gather list fails | NEW | NEW | No
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors seen while running test. | NEW | NEW | No
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress. | ASSI | ASSI | No
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) | NEW | NEW | No
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | NEW | NEW | No
2450 | min | P5 | RHEL | sean.hefty@intel.com | NEW | rping server exits with error message |  | NEW | Yes

## 2013-10-27
ID | Sev | Pri | OS | Assignee | Status | Summary
2418 | nor | P5 | Othe | arlin.r.davis@intel.com | NEW | dapltest with 100000 iterations and 150 threads hangs and packets do not transfer between client and server
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16
2416 | nor | P5 | Othe | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2
2419 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5
2423 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails
2420 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5
2422 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails
2415 | nor | P5 | Cent | ira.weiny@intel.com | ASSI | [OFED-3.5] infiniband-diags fails to build on Centos 6.3/6.4
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails
2375 | enh | P2 | SLES | tom@opengridcomputing.com | NEW | NFSoRDMA support required for SLES11sp2, RHEL6u2 & RHEL6u3.
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version.
2403 | maj | P1 | Othe | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os.
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-10-13 | 2013-10-27 | Change | Comment
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version. | 2012-11-12 | NEW | NEW | No
2403 | maj | P1 | Other | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os. | 2012-11-12 | ASSI | ASSI | No
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config | 2013-03-12 | NEW | NEW | No
2419 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5 | 2013-03-25 | REOP | REOP | No
2420 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5 | 2013-03-25 | REOP | REOP | No
2422 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails | 2013-04-02 | REOP | REOP | No
2423 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails | 2013-04-02 | REOP | REOP | No
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16 | 2013-04-09 | NEW | NEW | No
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails | 2013-04-22 | NEW | NEW | No
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2 | 2013-08-19 | NEW | NEW | No
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-10-13 | 2013-10-27 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | ASSI | duplicate member error when building infinipath-psm-3.1-364.1140 | 2013-04-29 | NEW | ASSI | Yes
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-10-13 | 2013-10-27 | Change
2439 | maj | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapl Pipeline test with RDMA Write and scatter gather list fails | 2013-07-24 | NEW | FIXED | Yes
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors - iWARP | 2013-08-13 | NEW | NEW | No
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress - iWARP | 2013-08-29 | ASSI | ASSI | No
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) - iWARP | 2013-09-24 | NEW | NEW | No
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | 2013-09-26 | NEW | NEW | No
2450 | min | P5 | RHEL | sean.hefty@intel.com | NEW | rping server exits with error message | 2013-10-15 | NEW | NEW | No
[8 empty] | NEW | 9
[8 empty] | ASSI | 3
[8 empty] | REOP | 4
[8 empty] | FIXED | 1
[8 empty] | WONTFIX | 0
[8 empty] | Total | 17

## 2013-10-28
ID | Sev | Pri | OS | Assignee | Status | Summary
2418 | nor | P5 | Othe | arlin.r.davis@intel.com | NEW | dapltest with 100000 iterations and 150 threads hangs and packets do not transfer between client and server
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16
2416 | nor | P5 | Othe | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2
2419 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5
2423 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails
2420 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5
2422 | maj | P5 | Othe | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails
2415 | nor | P5 | Cent | ira.weiny@intel.com | ASSI | [OFED-3.5] infiniband-diags fails to build on Centos 6.3/6.4
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails
2375 | enh | P2 | SLES | tom@opengridcomputing.com | NEW | NFSoRDMA support required for SLES11sp2, RHEL6u2 & RHEL6u3.
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version.
2403 | maj | P1 | Othe | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os.
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-10-13 | 2013-10-28 | Change | Comment
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version. | 2012-11-12 | NEW | NEW | No
2403 | maj | P1 | Other | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os. | 2012-11-12 | ASSI | ASSI | No
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config | 2013-03-12 | NEW | NEW | No
2419 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5 | 2013-03-25 | REOP | REOP | No
2420 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5 | 2013-03-25 | REOP | REOP | No
2422 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails | 2013-04-02 | REOP | REOP | No
2423 | maj | P5 | Other | idos@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails | 2013-04-02 | REOP | REOP | No
2425 | maj | P5 | Fedo | arlin.r.davis@intel.com | NEW | dapl/compat-dapl compilation fails on Fedora Core 16 | 2013-04-09 | NEW | FIXED | Yes | Will be released in the dapl 2.0.40-1 package
2429 | cri | P5 | Cent | jackm@mellanox.co.il | NEW | /etc/init.d/openibd start ---> fails | 2013-04-22 | NEW | WONTFIX | Yes | CentOS 5.x is not supported by OFED-3.5
2443 | enh | P5 | SLES | eli@mellanox.co.il | NEW | No TCP/UDP traffic on Connected mode on SLES11.2 | 2013-08-19 | NEW | FIXED | Yes | Vladimir Sokolovsky
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-10-13 | 2013-10-28 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | ASSI | duplicate member error when building infinipath-psm-3.1-364.1140 | 2013-04-29 | NEW | ASSI | Yes
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-10-13 | 2013-10-28 | Change
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors - iWARP | 2013-08-13 | NEW | NEW | No
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress - iWARP | 2013-08-29 | ASSI | ASSI | No
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) - iWARP | 2013-09-24 | NEW | NEW | No
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | 2013-09-26 | NEW | NEW | No
2450 | min | P5 | RHEL | sean.hefty@intel.com | NEW | rping server exits with error message | 2013-10-15 | NEW | NEW | No
[8 empty] | NEW | 6
[8 empty] | ASSI | 3
[8 empty] | REOP | 4
[8 empty] | FIXED | 2
[8 empty] | WONTFIX | 1
[8 empty] | Total | 16

## 2013-11-05
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-10-28 | 2013-11-05 | Change | Comment
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version - iWARP | 2012-11-12 | NEW | NEW | No
2403 | maj | P1 | Other | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os. | 2012-11-12 | ASSI | ASSI | No
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config | 2013-03-12 | NEW | NEW | No
2419 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5 | 2013-03-25 | REOP | REOP | No | Working to implement patch
2420 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5 | 2013-03-25 | REOP | REOP | No | Working to implement patch
2422 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails | 2013-04-02 | REOP | REOP | No | Working to implement patch
2423 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails | 2013-04-02 | REOP | REOP | No | Working to implement patch
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-10-28 | 2013-11-05 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | ASSI | duplicate member error when building infinipath-psm-3.1-364.1140 | 2013-04-29 | NEW | ASSI | Yes | Updated is targeted for OFED 3.12
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-10-28 | 2013-11-05 | Change
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors - iWARP | 2013-08-13 | NEW | NEW | No
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress - iWARP | 2013-08-29 | ASSI | ASSI | No
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) - iWARP | 2013-09-24 | NEW | NEW | No
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | 2013-09-26 | NEW | NEW | No
2450 | min | P5 | RHEL | sean.hefty@intel.com | NEW | rping server exits with error message | 2013-10-15 | NEW | NEW | No
2452 | blo | P1 | RHEL | jackm@mellanox.co.il | NEW | ibv_reg_mr taking excessive time in OFED | 2013-10-30 | NEW | FIXED | Yes | Resolved by Firmware update
[8 empty] | NEW | 6
[8 empty] | ASSI | 3
[8 empty] | REOP | 4
[8 empty] | FIXED | 1
[8 empty] | WONTFIX | 0
[8 empty] | Total | 14

## 2013-11-11
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-05 | 2013-11-11 | Change | Comment
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version - iWARP | 2012-11-12 | NEW | NEW | No | Open for 1 year now
2403 | maj | P1 | Other | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os. | 2012-11-12 | ASSI | ASSI | No | Open for 1 year now
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config | 2013-03-12 | NEW | NEW | No | No activity since 7/4/2013
2419 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5 | 2013-03-25 | REOP | REOP | No | Working to implement patch - 10/28/2013
2420 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5 | 2013-03-25 | REOP | REOP | No | Working to implement patch - 10/28/2013
2422 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails | 2013-04-02 | REOP | REOP | No | Working to implement patch - 10/28/2013
2423 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails | 2013-04-02 | REOP | REOP | No | Working to implement patch - 10/28/2013
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-05 | 2013-11-11 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | ASSI | duplicate member error when building infinipath-psm-3.1-364.1140 | 2013-04-29 | ASSI | ASSI | No | Updated is targeted for OFED 3.12
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-05 | 2013-11-11 | Change
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors - iWARP | 2013-08-13 | NEW | NEW | No | Vipul has been asked to help 9/30/2013
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress - iWARP | 2013-08-29 | ASSI | ASSI | No | Vipul has been asked to help 9/30/2013
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) - iWARP | 2013-09-24 | NEW | NEW | No | Caused by the commit 54d5fb2180f6f27141455d5252d26f40fd04d28f
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | 2013-09-26 | NEW | NEW | No | Jeff working with Pradeep & OFA Cluster
2450 | min | P5 | RHEL | sean.hefty@intel.com | NEW | rping server exits with error message | 2013-10-15 | NEW | NEW | No
2452 | blo | P1 | RHEL | jackm@mellanox.co.il | NEW | ibv_reg_mr taking excessive time in OFED | 2013-10-30 | NEW | NEW | No | Firmware update helped but still a problem
2453 | enh | P1 | RHEL | vlad@mellanox.co.il | NEW | OFED-3.5.2-rc2 fails to build on RHEL 6.4 kver 2.6.32-358.23.2.el6.x86_64 | 2013-11-08 |  | NEW | Yes
[8 empty] | NEW | 8
[8 empty] | ASSI | 3
[8 empty] | REOP | 4
[8 empty] | FIXED | 0
[8 empty] | WONTFIX | 0
[8 empty] | Total | 15

## 2013-11-24
Updated Bugs
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-11 | 2013-11-24 | Change | Comment
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version - iWARP | 2012-11-12 | NEW | LATER | Yes | Chelsio: Target Release 3.13
2403 | maj | P1 | Other | vlad@mellanox.co.il | ASSI | OFED installation is failing on freshly installed RHEL6.2 os. | 2012-11-12 | ASSI | WONTFIX | Yes | OFED should not silently uninstall RPMs that are not a part of it.
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config | 2013-03-12 | NEW | NEW | No | No activity since 7/4/2013
2419 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_write_bw -R and -z options fail in OFED-3.5 | 2013-03-25 | REOP | Fixed | Yes | resolved in perftest-2.0-0.60.g24e761d.tar.gz
2420 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_read_lat with -R and -z options fail in OFED-3.5 | 2013-03-25 | REOP | Fixed | Yes | resolved in perftest-2.0-0.60.g24e761d.tar.gz
2422 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_atomic_bw with -R and -z options fails | 2013-04-02 | REOP | Fixed | Yes | resolved in perftest-2.0-0.60.g24e761d.tar.gz
2423 | maj | P5 | Other | gilr@dev.mellanox.co.il | REOP | ib_atomic_lat with -R and -z options fails | 2013-04-02 | REOP | Fixed | Yes | resolved in perftest-2.0-0.60.g24e761d.tar.gz
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-11 | 2013-11-24 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | ASSI | duplicate member error when building infinipath-psm-3.1-364.1140 | 2013-04-29 | ASSI | LATER | Yes | Updated is targeted for OFED 3.12
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-11 | 2013-11-24 | Change
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors - iWARP | 2013-08-13 | NEW | LATER | Yes | Chelsio: Target Release 3.13
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress - iWARP | 2013-08-29 | ASSI | LATER | Yes | Chelsio: Target Release 3.13
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) - iWARP | 2013-09-24 | NEW | ASSI | Yes | Caused by the commit 54d5fb2180f6f27141455d5252d26f40fd04d28f
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | 2013-09-26 | NEW | ASSI | Yes | Accounts setup for Jeff & Tom on 11/13/2013
2450 | min | P5 | RHEL | sean.hefty@intel.com | NEW | rping server exits with error message | 2013-10-15 | NEW | Fixed | Yes | Fixed in upstream code and a new 1.0.17.1 release.
2452 | blo | P1 | RHEL | jackm@mellanox.co.il | NEW | ibv_reg_mr taking excessive time in OFED | 2013-10-30 | NEW | ASSI | Yes | Yishai Hadas from Mellanox working on it
2453 | enh | P1 | RHEL | vlad@mellanox.co.il | NEW | OFED-3.5.2-rc2 fails to build on RHEL 6.4 kver 2.6.32-358.23.2.el6.x86_64 | 2013-11-08 | NEW | Fixed | Yes | Vlad fixed in OFED-3.5-2-20131120-0307.tgz
OFED 3.12 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-11 | 2013-11-24 | Change
2454 | blo | P5 | RHEL | Pradeep.Kankipati@Emulex.Com | NEW | libocrdma-0.0.1-1 rpmbuild fails | 2013-11-11 | NEW | NEW | No
| nor | 4 | [5 empty] | ASSI | 3
| blo | 2 | [5 empty] | FIXED | 6
| cri | 2 | [5 empty] | LATER | 4
| maj | 6 | [5 empty] | NEW | 2
| min | 1 | [5 empty] | REOP | 0
| enh | 1 | [5 empty] | WONTFIX | 1
| Total | 16 | [5 empty] | Total | 16
Open Bugs Only
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-11 | 2013-11-24 | Change | Comment
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version - iWARP | 2012-11-12 | NEW | LATER | Yes | Chelsio: Target Release 3.13
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config | 2013-03-12 | NEW | NEW | No | No activity since 7/4/2013
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-11 | 2013-11-24 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | ASSI | duplicate member error when building infinipath-psm-3.1-364.1140 | 2013-04-29 | ASSI | LATER | Yes | Updated is targeted for OFED 3.12
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-11 | 2013-11-24 | Change
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors - iWARP | 2013-08-13 | NEW | LATER | Yes | Chelsio: Target Release 3.13
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress - iWARP | 2013-08-29 | ASSI | LATER | Yes | Chelsio: Target Release 3.13
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) - iWARP | 2013-09-24 | NEW | ASSI | Yes | Caused by the commit 54d5fb2180f6f27141455d5252d26f40fd04d28f
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | 2013-09-26 | NEW | ASSI | Yes | Accounts setup for Jeff & Tom on 11/13/2013
2452 | blo | P1 | RHEL | jackm@mellanox.co.il | NEW | ibv_reg_mr taking excessive time in OFED | 2013-10-30 | NEW | ASSI | Yes | Yishai Hadas from Mellanox working on it
OFED 3.12 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-11 | 2013-11-24 | Change
2454 | blo | P5 | RHEL | Pradeep.Kankipati@Emulex.Com | NEW | libocrdma-0.0.1-1 rpmbuild fails | 2013-11-11 | NEW | NEW | No
| nor | 4 | [5 empty] | ASSI | 3
| blo | 2 | [5 empty] | FIXED | 0
| cri | 2 | [5 empty] | LATER | 4
| maj | 1 | [5 empty] | NEW | 2
| min | 0 | [5 empty] | REOP | 0
| enh | 0 | [5 empty] | WONTFIX | 0
| Total | 9 | [5 empty] | Total | 9

## 2013-11-25
Updated Bugs
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-24 | 2013-11-25 | Change | Comment
2402 | nor | P1 | SLES | vipul@chelsio.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version - iWARP | 2012-11-12 | LATER | LATER | No | Chelsio: Target Release 3.13
2416 | nor | P5 | Other | eli@mellanox.co.il | NEW | Not able to configure RoCEE Ethernet port on IB QDR adapter using /sbin/connectx_port_config | 2013-03-12 | NEW | WONTFIX | Yes | Vlad believes this was due to traffic on the connection when the call was made
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-24 | 2013-11-24 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | ASSI | duplicate member error when building infinipath-psm-3.1-364.1140 | 2013-04-29 | LATER | LATER | No | Updated is targeted for OFED 3.12
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-24 | 2013-11-24 | Change
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors - iWARP | 2013-08-13 | LATER | LATER | No | Chelsio: Target Release 3.13
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress - iWARP | 2013-08-29 | LATER | LATER | No | Chelsio: Target Release 3.13
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) - iWARP | 2013-09-24 | ASSI | ASSI | No | Will be part of dapl 2.0.40 which may not be part of 3.5-2 GA
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | 2013-09-26 | ASSI | ASSI | No | Accounts setup for Jeff & Tom on 11/13/2013
2452 | blo | P1 | RHEL | jackm@mellanox.co.il | NEW | ibv_reg_mr taking excessive time in OFED | 2013-10-30 | ASSI | ASSI | No | Yishai Hadas from Mellanox working on it
OFED 3.12 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-24 | 2013-11-24 | Change
2454 | blo | P5 | RHEL | Pradeep.Kankipati@Emulex.Com | NEW | libocrdma-0.0.1-1 rpmbuild fails | 2013-11-11 | NEW | NEW | No
| nor | 4 | [5 empty] | ASSI | 3
| blo | 2 | [5 empty] | FIXED | 0
| cri | 2 | [5 empty] | LATER | 4
| maj | 1 | [5 empty] | NEW | 1
| min | 0 | [5 empty] | REOP | 0
| enh | 0 | [5 empty] | WONTFIX | 1
| Total | 9 | [5 empty] | Total | 9

## 2013-12-08
Updated Bugs
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-25 | 2013-12-08 | Change | Comment
2402 | nor | P1 | SLES | swise@opengridcomputing.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version - iWARP | 2012-11-12 | LATER | LATER | No | Chelsio: Target Release 3.13
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-24 | 2013-12-08 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | ASSI | duplicate member error when building infinipath-psm-3.1-364.1140 | 2013-04-29 | LATER | LATER | No | Update is targeted for OFED 3.12
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-24 | 2013-12-08 | Change
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors - iWARP | 2013-08-13 | LATER | LATER | No | Chelsio: Target Release 3.13
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress - iWARP | 2013-08-29 | LATER | LATER | No | Chelsio: Target Release 3.13
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) - iWARP | 2013-09-24 | ASSI | ASSI | No | Will be part of dapl 2.0.40 which may not be part of 3.5-2 GA
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | 2013-09-26 | ASSI | ASSI | No | Pradeep, Jeff and Tom Tucker working on it
2452 | blo | P1 | RHEL | jackm@mellanox.co.il | NEW | ibv_reg_mr taking excessive time in OFED | 2013-10-30 | ASSI | Fixed | Yes | Yishai Hadas from Mellanox working on it
OFED 3.12 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-11-24 | 2013-12-08 | Change
2454 | blo | P5 | RHEL | Pradeep.Kankipati@Emulex.Com | NEW | libocrdma-0.0.1-1 rpmbuild fails | 2013-11-11 | NEW | Fixed | Yes | Pradeep checkd in libocrdma-1.0.1.tar.gz
| nor | 3 | [5 empty] | ASSI | 2
| blo | 2 | [5 empty] | FIXED | 2
| cri | 2 | [5 empty] | LATER | 4
| maj | 1 | [5 empty] | NEW | 0
| min | 0 | [5 empty] | REOP | 0
| enh | 0 | [5 empty] | WONTFIX | 0
| Total | 8 | [5 empty] | Total | 8

## 2013-12-13
Updated Bugs
OFED 3.5 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-12-08 | 2013-12-13 | Change | Comment
2402 | nor | P1 | SLES | swise@opengridcomputing.com | NEW | Modinfo of cxgb4 does not show 'ofed' in driver version - iWARP | 2012-11-12 | LATER | LATER | No | Chelsio: Target Release 3.13
OFED 3.5-1 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-12-08 | 2013-12-13 | Change
2430 | nor | P5 | Other | mike.marciniszyn@intel.com | ASSI | duplicate member error when building infinipath-psm-3.1-364.1140 | 2013-04-29 | LATER | LATER | No | Update is targeted for OFED 3.12
OFED 3.5-2 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-12-08 | 2013-12-13 | Change
2441 | cri | P1 | Other | arlin.r.davis@intel.com | NEW | "RDMA/RD-reaping DTO problem, status = FAILURE" errors - iWARP | 2013-08-13 | LATER | LATER | No | Chelsio: Target Release 3.13
2445 | cri | P5 | SLES | swise@opengridcomputing.com | NEW | dapltest -performance stalls on running stress - iWARP | 2013-08-29 | LATER | LATER | No | Chelsio: Target Release 3.13
2448 | nor | P5 | RHEL | arlin.r.davis@intel.com | NEW | dapltest with test type Quit doesn't work with ofa-v2-iwarp (intel ne020 rnic) - iWARP | 2013-09-24 | ASSI | ASSI | No | Will be part of dapl 2.0.40 which may not be part of 3.5-2 GA
2449 | maj | P5 | RHEL | becker@nas.nasa.gov | NEW | Power 7 machine crashes when trying to do NFSoRDMA mount in OFED-3.5-2-rc1 | 2013-09-26 | ASSI | ASSI | No | Pradeep, Jeff and Tom Tucker working on it
OFED 3.12 | Sev | Pri | OS | Assignee | Status | Summary | Opened | 2013-12-08 | 2013-12-13 | Change
| nor | 3 | [5 empty] | ASSI | 2
| blo | 0 | [5 empty] | FIXED | 0
| cri | 2 | [5 empty] | LATER | 4
| maj | 1 | [5 empty] | NEW | 0
| min | 0 | [5 empty] | REOP | 0
| enh | 0 | [5 empty] | WONTFIX | 0
| Total | 6 | [5 empty] | Total | 6