## Slide 1: OFED 1.x Roadmap & Release Process
November 06
Jeff Squyres, Woodruff, Robert J,
Betsy Zeller, Tziporet Koren,
Notes: <number>

## Slide 2: OFED 1.x Support
Issue reporting on bugzilla:
  http://openfabrics.org/bugzilla/
Support on Wiki page:
  https://openib.org/tiki/tiki-index.php?page=OFED+Support
  Need a page on openfabrics.org web site
  New patches can be placed under https://openib.org/svn/gen2/branches/1.1/ofed/support/
Minor version can be provided by any company
  E.g. OFED 1.1.1 by IBM
Open: Do we want common 1.1.x release for major bug fixes and maintenance
  e.g. libibverbs 1.0.4, IPoIB HA oops, etc.
  If yes who is going to QA such a release

## Slide 3: OFED 1.x Release Template
Options:
  Time driven
  Features driven
Suggestion: Combination
  Have a list of features and see what can fit to Q1 time frame
  Get to consensus on priorities today
  All maintainers send estimation by Dec-1
  Close features list in Dec-4

## Slide 4: High Level Goals
Be incorporated into enterprise distro
  RedHat EL5, SLES10
  Minimize integration effort into distribution
  Fit with distribution schedule
Daily regression tests (at least for compile)
Defined and agreed on release criteria
QoS
Scalability (# nodes, # connections)
High availability (define for each component)
Easier end-user customization (e.g., patching)

## Slide 5: OFED 1.2 Features - Core
Core:
  SA cache
  Multicast
CMA:
  QoS
  APM support
  Multicast

## Slide 6: OFED 1.2 Features - Libraries
Use a stable release that each maintainer provides
  Need a stable release for libibcm, librdmacm and libumad
libibverbs 1.1: (Roland)
  Fork support (requires apps change)
  Memory windows
  Reregister memory region (incl. extend without unregister...)
  Minor ABI extensions for new low-level drivers
  Better low-level driver handling, including multiple drivers linked in statically.
  Open: Do we want libibverbs 1.0 included too?
libibcm 1.0 (Sean)
librdmacm 1.0 (Sean)
libumad 1.0 (Hal)

## Slide 7: OFED 1.2 Features - ULPs
IPoIB: NAPI, Connected Mode
SDP: Netstat, scalability, small messages BW
iSER: No new features
SRP: MPP integration for HA
RDS: First integration (assuming dual license)
uDAPL: No major features

## Slide 8: OFED 1.2 Features - Management
OpenSM:
  FAT tree routing
  QoS
Diagnostics:
  Monitoring QoS
  Partitions analysis
  GUI tool

## Slide 9: OFED 1.2 Features - MPI
Common MPI setup sourcing
  mpivars.sh / mpivars.csh
MVAPICH: Version 0.9.9
Open MPI: depends on the OFA code freeze date
  Possible: v1.2
  Other possible: v1.1.3 and v1.2b<something> as tech preview

## Slide 10: OFED 1.2 OS Matrix
OS Matrix closure: 4 weeks before the release
kernel.org: latest kernel available + previous released one
Novell:
  SLES 9 SP3
  SLES 10 (SP1)
Redhat:
  RHEL 4 (up?)
  RHEL 5?
What about free distros (e.g. Fedora, SuSE Pro, …)
  Decision was not to QA any free distro

## Slide 11: OFED 1.2 Sources
Kernel:
  Start based on Roland’s tree for 2.6.19
    May need to move to 2.6.20 when first RC is out
  Backport – port to supported kernels (added by OFED)
  Add out of kernel modules: SDP, RDS?, uCMA
  git tree under the new server
    To be set next week
User:
  Ongoing based on user trunk
    Start with svn and move to git when available
  Based on official releases provided by maintainers
Daily build of both kernel and user on the server
  Enable easy developer testing
  Regression testing run daily – does companies committed to this?

## Slide 12: OFED 1.x Timeline
Agree on release features:
  immediately after a release is done
Alpha / feature freeze: 11 weeks ahead the release
Beta: 3 weeks after Alpha
1st RC: 4 weeks after Beta
2nd RC: 2 weeks after RC1
Release: 2 weeks after RC2

## Slide 13: OFED 1.2 Timeline Example
Release: Apr 18 (beginning Q2’07)
2nd RC: Apr 2
1st RC: Mar 21
Beta: Feb 28
Alpha / feature freeze: Jan 31
Feature list agreed Dec 4